TIMELINE FOR LIBRARY MILLENIUM COMMITTEE PROJECT:

By 4/12:		 Appoint Library Millenium Project team members.

By 4/25:		Charge handoff from LFA chair to Millenium Project team.

By 5/30:              	Review Millenium Project Report, the Grace Project report                                  and other campus documents .

5/23 – 9/26 		Collect and identify issues from existing data

- Staff Environment Survey

- Salary data for UA Library

- ARL Data and report

- Library Faculty Assembly Issues document.

- Career progression/merit recipients.

- Fitness Report.

- Current Situation Analysis

- Library Affirmative Action reports

- Exit Interview information.

- Library Diversity Statement.

- Promotion and Continuing Status data

- New Employee Orientation survey

8/29-10/17		 Develop survey instrument:

- 8/29--9/6: finish reviewing issues pulled from documents.

- 9/9-- 9/20: cluster issues around thematic topics using affinity diagram technique

- 9/23--10/4: develop questions for survey

- 10/7--10/18: pre-test survey with focus groups or some other way

- 10/21--11/1: clean up survey and prepare for distribution

November 	 	Administer survey

# Dec/Jan :   		Analyze results and prepare report

Specify goals and actions requiring policy changes or needed changes in practices.

Publicize exisiting policies to promote equity.

Develop plans and designate individuals/implementation.